## Equality Scheme Action Plan
EQUALITY SCHEME ACTION PLAN 2021 - 2024
EQUALITY OBJECTIVES - KEY AREAS | OBJECTIVE | ACTIONS | LEAD OFFICER | TARGET DATE | PROGRESS/COMMENTS
1. LEADERSHIP AND CORPORATE COMMITMENT | Councillors and senior managers to be aware of the equality profile of the residents of the borough. To include considering the impact of equality and diversity as a key part of the preparation before implementing any changes, decisions, or policies. | Establish the current processes that services take with regard to equality and diversity in decision making. To include identifying where EIAs are routinely either being undertaken or not | Specialist Legal (Solicitor Employment and Litigation), Senior Policy Officer - Community and Events | To be determined by E&D group | To embrace in service planning - Strategy and Communications Manager may be able to advise
|  | To enable the above, all managers must understand how to assess impact on equality through improving guidance, training and awareness of the equality impact assessment. This will lead to managers conducting meaningful and consistent assessments to inform senior management decision making. | Specialist - HR (Business Partner), Specialist - HR (Training) | April 2023 | Improved guidance on assessing impact on equality and a new EIA form was produced and published in April 2019 and was approved by the E&D Group. Video on 'how to' is being planned for managers as a step by step guide - FC to contact Mel - invite to future mtgs Service Leaders underwent training in their regular meeting on 17 March 2022 Equality & Diversity training - Hannah looking at training programme (Gfd, Waverley & future options) - to present to Tom Horwood - planned for early October - looking at a mixed provision of online and face-to-face provision or combined offering with WBC
|  | Publish data gathered in a useful and meaningful but not onerous way and find ways to do this efficiently and in a timely manner. |  | August 2022 | HR to check progress with Comms- do KPIs include E&D, Council communications KPI workshop on 19 Sept so if new KPI suggested, can be discussed by Exec then
|  | KPI's being planned specifically on ED&I in addition to the workforce profile data already published on the internet. |  | August 2022 | Ongoing - Ali working on publishing new workforce data profile
2. SERVICE DELIVERY AND CUSTOMER CARE | Make use of data collated from (customer) equality monitoring to ensure that it is published on the website annually, and used to establish the impact on equality and inform the quality of EIAs. To include ensuring that barriers to services, including all Council communications, are accessible to people who have protected characteristics. | Ensure that managers complete meaningful and sensitive EIA when planning changes and where an impact is identified they amend the proposal to remove or reduce the adverse impact, or evidence that the impact is justified. | Service Leaders, Customer Service Team Leader | Ongoing | HR and Legal pick up when an EIA hasn't been completed as they are approvers for any proposals but managers must take individual responsibility for this when conducting EIAs Refresher training for EIAs - Ian was going to check this - Hannah to follow-up and maybe have a couple of sessions a year - maybe a Comms note advising of what is available - suggest Ali/Hannah/FC could do the sessions Need to check where EIA info is on the intranet - under the Policies area
|  | Continue with process for monitoring customer complaints and compliments from people in protected groups or for complaints of harassment or discrimination |  | Ongoing | HR Specialists receive weekly alerts of all complaints outstanding and can pick up any equality related issues. Customer Services Team Leader, to alert HR when any equality related complaints are received. These will be monitored and any appropriate action taken. None received at the time of writing. Assume will come via Ali but FC to check
|  | Website is reviewed to ensure it meets the needs of protected groups | Web Team | Jan 23 | An accessibility audit was carried out in 2021/2022 which informed the actions taken to ensure the website is accessible. This is progressing well Web team reviewing documents to ensure complient and accessible. Guidance will be produced for the whole Council on accessibility of documents in due course.
|  | Ensure equality information is included in customer satisfaction surveys | E&D group | December 2022 | Hannah and Ali working on general customer surveys - to include E&D. JB to review CSAT survey to ensure equalities data gathering is included. Equalities data is also gathered as a matter of course on websurveys.
|  | Update E&D info on Business World - include alternative pronouns for non binary | led by HR via whole staff email update BW | December 2022 | No progress due to other time constraints etc - AH following up
|  | Use workforce profiling to assess the data and compare to the profile of our customers. Complete and publish workforce profile | Specialist - HR (Business Partner) | January 2023 | Workforce profile completed for 20/21 and published - next one due Jan 23
3. EMPLOYMENT AND TRAINING | Establish where there are inequalities in the workforce profile and take action, if appropriate, to resolve. Ensure that training is relevant, timely and available to all staff. | Regularly review pay and benefits to ensure equitable across all staff. To include ensuring the job evaluation scheme and appeals process are appropriate and fair. | Lead Specialist - HR | ongoing | Council wide job evaluation was completed before the Future Guildford programme. This will be reviewed once the new structure has been transitioned and all staff are in post. Ongoing process to align with WBC (inc. agile working, job evaluation)
| Ensure that staff are paid fairly and equitably | Annual review of the Pay Policy | Lead Specialist - HR | Annual ongoing
|  | Annual gender pay gap analysis to identify the mean and median differences in pay between the genders | Lead Specialist - HR | Annual ongoing | The Gender Pay Gap is analysed annually and following approval from the Corporate Governance & Standards Committee the report is published on the Government's Equality website and the transparency pages of the Council's website. The gap is currently positive.
| Ensure that all staff understand the impact of equality and diversity in the workplace. | Ensure recruitment training is in place for newly appointed managers and as a refresher, provided or arranged by HR. | Comms team, HR | December 2022 | Considering an external training provider for Safer Recruitment training to include E&D sections - follow-up with Ali Considering online alternatives for Safer Recruitment and E&D. Working on video training for a variety of subjects including EIAs, recruitment and E&D
|  | HR to undertake Equality, Diversion and Inclusion NVQ Level 2 again as a refresher. Then roll out to the rest of the organisation | HR | April 2023 | No progress due to changes within the team - need to agree new action date Review in line with future HR provision across both councils
|  | Ensure that the Council's equality and diversity forum meet regularly to ensure a Council wide approach and awareness. | E&D group. | Ongoing | E&D group in place, terms of reference established. First meeting 16/4, 12 weekly thereafter. To invite Ian Doyle as chair of the group (or new Executive Head of Organisational Development)
| Be a Disability Confident (formerly 'two ticks') employer | Review whether to apply for Disability Confident status. This objective will also include introducing appropriate training for staff from various different avenues in order to increase awareness of staff. | Specialist - HR (Business Partner), Specialist - HR (Training) | April 2023 | Mental Health First Aiders have been trained on fully 2 day course, details circulated and processes in place such as EAP Basic level disability confidence level achieved. To review whether we aim to achieve higher level.
| Increase the number of job applications from a more diverse range of candidates including those with protected characteristics | Investigate options and advertise on specialist diversity recruitment sites in order to reach a more diverse range of applicants | HR | December 2022 | We advertise all vacancies on CTP.org which is a jobsite for ex service personnel most of whom will possess one of the protected characteristics. More work to be done for other groups. Some progress made. Ali is researching currently with CIPD etc. Options include University of Surrey, diversity friendly language in adverts, possible media depending on costs.
4. CONSULTATION AND COMMUNITY DEVELOPMENT | Encourage various communities to engage with the Council on equality matters, including actively encouraging protected groups to participate in consultations | This will involve encouraging service leaders to engage in being proactive in consultations. It will also be achieved by managers engaging with members of protected groups when conducting EIAs. | E&D group. Community Service Manager | Ongoing | We are currently extracting E&D data from the CSAT survey, Salesforce - no update as yet We have undertaken an assessment of diversity on the housing register which shows that ethnic minority applicants are accessing the register and being successfully housed. The data collected on the other equality strands shows some degree of diversity amonth our applicants. SK - Checking system or training issues (possibly in Case Services) for homeless - will be handed back to this service from February 2023 We have committed to include the Guildford Access Group in our consultations Our committe report template now includes a mandatory field for equality and a link to the EIA template and guidance notes - January 2022

## Sheet1
The general duty sets out three main aims. As a public body, we must have due regard to the need to:
· eliminate unlawful discrimination, harassment and victimisation and other conduct prohibited by the Act
· advance equality of opportunity between people who share a protected characteristic and those who do not
· foster good relations between people who share a protected characteristic and those who do not.
Equality and Diversity Forum
The Equality and Diversity Forum is a new employee group chaired by the Human Resources Partner (Equalities). The Forum aims to have representatives from across the protected characteristics as well as employees who have an interest in equality and diversity matters. The purpose of the Forum is to:
· monitor and review the Equality Scheme and the associated action plan
· support the Council in continuously improving equality and diversity practice
· support the Council in developing good equality practice
· assist the Council in embedding equality and diversity issues in the mind of every employee to the effect that it becomes part of the everyday work.
We will publish summaries of the equality impact assessments on our intranet and internet sites. EIA’s have been published in the past but this is an area that needs looking at and will be addressed within the action plan.
We are committed to carrying out impact assessments on our existing and proposed policies and procedures, services and functions to determine whether there are any equality implications. This is generally done using the Council’s Screening and Scoping Equality Impact Assessment (EIA) form and Full Equality Impact Assessment (EIA) form, where relevant. This method of assessment has been in place for some time and it would be useful to review it to decide whether an alternative method would be more ‘user-friendly’ and therefore produce more effective results. This will be reflected in the action plan.